## PaySky-Detailed Resources
Global Brands Group Azure Security Initial Finding and Recommendation-PaySky-Spoke Subscription
| Customer Name : Paysky |  | Global Brands Group
Customer Primary Contact Name : Omar Sameh
| Customer Primary Contact Email : Omar.Sameh@gbrands.com |  | Cloud Security Engineer Name: Omar Sameh
| Customer Secondary Contact Name : Sherif Nagy |  | Start Date : 2-3-2025
| Customer Secondary Contact Email : Sherif.Nagy@gbrands.com |  | Due Date :
| Start Date : 2-3-2025 |  | Cloud Security Team Lead: Marco Fekry
| Due Date : |  | Cloud Security Team Lead Email: Marco.Fekry@gbrands.com
Target Security Area | Detailed Resources Report Summary Findings | Severity
Storage accounts | gimpreprodsacc Storage Account Public Network Access should be disallowed, It is recommended to use private EndPoints to secure your data | High
Virtual Machines | AZ-VM-GIM-UAT-SRV-01 Virtual Machine Disabled Windows automatic Updates detected, It is recommended to turn automatic updates On | High
Virtual Machines | AZ-VM-GIM-UAT-SRV-01 Virtual Machine Disabled Windows Patch Mode detected, It is recommended to turn Patch Mode On | High
Virtual Machines | AZ-VM-GIM-UAT-SRV-01 Virtual Machine Disabled Windows Assessment Mode detected, It is recommended to turn Assessment Mode On | High
Virtual Machines | AZ-VM-GIM-UAT-SRV-01 Virtual Machine No Trusted Launch detected, It is recommended to enable Trusted Launch for Virtual machine security | High
Virtual Machines | AZ-VM-GIM-UAT-SRV-01 Virtual Machine Extension enablevmAccess Failed state detected, It is recommended to reconfigure the Failed Extension | High
Virtual Machines | AZ-VM-GIM-UAT-SRV-2 Virtual Machine Extension LinuxDiagnostic Failed state detected, It is recommended to reconfigure the Failed Extension | High
Virtual Machines | AZ-VM-GIM-UAT-SRV-02 Virtual Machine Disabled Linux Patch Mode detected, It is recommended to turn Patch Mode On | High
Virtual Machines | AZ-VM-GIM-UAT-SRV-02 Virtual Machine Disabled Linux Assessment Mode detected, It is recommended to turn Assessment Mode On | High
Virtual Machines | AZ-VM-GIM-UAT-SRV-02 Virtual Machine No Trusted Launch detected, It is recommended to enable Trusted Launch for Virtual machine security | High
Virtual Machines | AZ-VM-GIM-UAT-SRV-1 Virtual Machine Disabled Windows Assessment Mode detected, It is recommended to turn Assessment Mode On | High
Virtual Machines | AZ-VM-GIM-UAT-SRV-2 Virtual Machine Disabled Linux Patch Mode detected, It is recommended to turn Patch Mode On | High
Virtual Machines | AZ-VM-GIM-UAT-SRV-2 Virtual Machine Disabled Linux Assessment Mode detected, It is recommended to turn Assessment Mode On | High
Virtual Machines | AZ-VM-GIM-UAT-SRV-01 Virtual Machine Disks Encryption is recommended to secure your data | High
Virtual Machines | AZ-VM-GIM-UAT-SRV-02 Virtual Machine Disks Encryption is recommended to secure your data | High
Virtual Machines | AZ-VM-GIM-UAT-SRV-1 Virtual Machine Disks Encryption is recommended to secure your data | High
Virtual Machines | AZ-VM-GIM-UAT-SRV-2 Virtual Machine Disks Encryption is recommended to secure your data | High
Virtual Machines | AZ-VM-GIM-UAT-SRV-01 Virtual Machine Disks Replication is recommended for High Availability of your workloads | High
Virtual Machines | AZ-VM-GIM-UAT-SRV-02 Virtual Machine Disks Replication is recommended for High Availability of your workloads | High
Virtual Machines | AZ-VM-GIM-UAT-SRV-1 Virtual Machine Disks Replication is recommended for High Availability of your workloads | High
Virtual Machines | AZ-VM-GIM-UAT-SRV-2 Virtual Machine Disks Replication is recommended for High Availability of your workloads | High
SQL Servers | az-db-gim-preprod SQL Server Firewall Rules detected, It is recommended to harden the SQL Server Firewall for Security | High
SQL Databases | switch SQL Database Advanced Threat Protection disabled State detected, It is recommended to turn Advanced Threat Protection State On to secure your data | High
SQL Databases | switch SQL Database Data Masking disabled State detected, It is recommended to turn Data Masking State On to secure your data | High
SQL Databases | switch SQL Database has no SQL assessment deployed, It is recommended to turn SQL assessment On to keep track of your Database security | High
SQL Databases | GCS SQL Database Advanced Threat Protection disabled State detected, It is recommended to turn Advanced Threat Protection State On to secure your data | High
SQL Databases | GCS SQL Database Data Masking disabled State detected, It is recommended to turn Data Masking State On to secure your data | High
SQL Databases | GCS SQL Database has no SQL assessment deployed, It is recommended to turn SQL assessment On to keep track of your Database security | High
SQL Databases | Cube2Hangfire SQL Database Advanced Threat Protection disabled State detected, It is recommended to turn Advanced Threat Protection State On to secure your data | High
SQL Databases | Cube2Hangfire SQL Database Data Masking disabled State detected, It is recommended to turn Data Masking State On to secure your data | High
SQL Databases | Createlndex Advisor recommendations has been detected for the Database Cube2Hangfire | High
SQL Databases | Droplndex Advisor recommendations has been detected for the Database Cube2Hangfire | High
SQL Databases | DbParameterization Advisor recommendations has been detected for the Database Cube2Hangfire | High
SQL Databases | Defragmentlndex Advisor recommendations has been detected for the Database Cube2Hangfire | High
SQL Databases | ForceLastGoodPlan Advisor recommendations has been detected for the Database Cube2Hangfire | High
SQL Databases | Cube2Hangfire SQL Database has no SQL assessment deployed, It is recommended to turn SQL assessment On to keep track of your Database security | High
SQL Databases | cube2 SQL Database Advanced Threat Protection disabled State detected, It is recommended to turn Advanced Threat Protection State On to secure your data | High
SQL Databases | cube2 SQL Database Data Masking disabled State detected, It is recommended to turn Data Masking State On to secure your data | High
SQL Databases | Createlndex Advisor recommendations has been detected for the Database cube2 | High
SQL Databases | Droplndex Advisor recommendations has been detected for the Database cube2 | High
SQL Databases | DbParameterization Advisor recommendations has been detected for the Database cube2 | High
SQL Databases | Defragmentlndex Advisor recommendations has been detected for the Database cube2 | High
SQL Databases | ForceLastGoodPlan Advisor recommendations has been detected for the Database cube2 | High
SQL Databases | cube2 SQL Database has no SQL assessment deployed, It is recommended to turn SQL assessment On to keep track of your Database security | High
SQL Databases | VatCollectionRunTime SQL Database Advanced Threat Protection disabled State detected, It is recommended to turn Advanced Threat Protection State On to secure your data | High
SQL Databases | VatCollectionRunTime SQL Database Data Masking disabled State detected, It is recommended to turn Data Masking State On to secure your data | High
SQL Databases | VatCollectionRunTime SQL Database has no SQL assessment deployed, It is recommended to turn SQL assessment On to keep track of your Database security | High
SQL Databases | InvoiveCloudDb SQL Database Advanced Threat Protection disabled State detected, It is recommended to turn Advanced Threat Protection State On to secure your data | High
SQL Databases | lnvoiveCloudDb SQL Database Data Masking disabled State detected, It is recommended to turn Data Masking State On to secure your data | High
SQL Databases | InvoiveCloudDb SQL Database has no SQL assessment deployed, It is recommended to turn SQL assessment On to keep track of your Database security | High
SQL Databases | NBGDb SQL Database Advanced Threat Protection disabled State detected, It is recommended to turn Advanced Threat Protection State On to secure your data | High
SQL Databases | NBGDb SQL Database Data Masking disabled State detected, It is recommended to turn Data Masking State On to secure your data | High
SQL Databases | NBGDb SQL Database Audit disabled detected, It is recommended to turn Audit On to keep track of your databases | High
SQL Databases | NBGDb SQL Database has no SQL assessment deployed, It is recommended to turn SQL assessment On to keep track of your Database security | High
SQL Databases | Cube2Hangfire_POS SQL Database Advanced Threat Protection disabled State detected, It is recommended to turn Advanced Threat Protection State On to secure your data | High
SQL Databases | Cube2Hangfire_POS SQL Database Data Masking disabled State detected, It is recommended to turn Data Masking State On to secure your data | High
SQL Databases | Cube2Hangfire_POS SQL Database Audit disabled detected, It is recommended to turn Audit On to keep track of your databases | High
SQL Databases | Cube2Hangf\re_POS SQL Database has no SQL assessment deployed, It is recommended to turn SQL assessment On to keep track of your Database security | High
SQL Databases | InvoiceHostDb SQL Database Advanced Threat Protection disabled State detected, It is recommended to turn Advanced Threat Protection State On to secure your data | High
SQL Databases | lnvoiceHostDb SQL Database Data Masking disabled State detected, It is recommended to turn Data Masking State On to secure your data | High
SQL Databases | lnvoiceHostDb SQL Database Audit disabled detected, It is recommended to turn Audit On to keep track of your databases | High
SQL Databases | InvoiceHostDb SQL Database has no SQL assessment deployed, It is recommended to turn SQL assessment On to keep track of your Database security | High
SQL Databases | VatCollectionDb SQL Database Advanced Threat Protection disabled State detected, It is recommended to turn Advanced Threat Protection State On to secure your data | High
SQL Databases | VatCollectionDb SQL Database Data Masking disabled State detected, It is recommended to turn Data Masking State On to secure your data | High
SQL Databases | VatCollectionDb SQL Database Audit disabled detected, It is recommended to turn Audit On to keep track of your databases | High
SQL Databases | VatCollectionDb SQL Database has no SQL assessment deployed, It is recommended to turn SQL assessment On to keep track of your Database security | High
SQL Databases | CubeToken SQL Database Advanced Threat Protection disabled State detected, It is recommended to turn Advanced Threat Protection State On to secure your data | High
SQL Databases | CubeToken SQL Database Data Masking disabled State detected, It is recommended to turn Data Masking State On to secure your data | High
SQL Databases | CubeToken SQL Database Audit disabled detected, It is recommended to turn Audit On to keep track of your databases | High
SQL Databases | CubeToken SQL Database has no SQL assessment deployed, It is recommended to turn SQL assessment On to keep track of your Database security | High
Load Balancers | kubernetes Public Load Balancer has been detected, It is recommended to change the load Balncer type from Public to Private to secure your Workloads | High
Load Balancers | kubernetes No Logs has been detected, It is recommended to enable Diagnostics to keep track of your LoadBalancer insights | High
Load Balancers | kubernetes-internal No Logs has been detected, It is recommended to enable Diagnostics to keep track of your LoadBalancer insights | High
Key Vault | GIMPAY-KVO1 Key Vault Public Access has been detected, It is recommended to use private connectivity to secure your workloads | High
Key Vault | GIMPAY-KVO1 Key Vault Soft Delete has been detected, It is recommended to disable Soft Delete to secure your Key Vault | High
Key Vault | GIMPAY-KVO1 Key Vault no RBAC Authorization detected, It is recommended to use RBAC AuthorizatiOn to secure your Key Vault | High
Monitor Alert | GlM-PreProd_Create-Update-Network-Security-Group Moniotr Alert has been detected on resource | Medium
Monitor Alert | GIM-PreProd_Create-Update-Public-IP-Address-rule Moniotr Alert has been detected on resource | Medium
Monitor Alert | GlM-PreProd_DeIete-Public-IP-Address Moniotr Alert has been detected on resource | Medium
Monitor Alert | Backup Failure Moniotr Alert has been detected on resource AZ-VM-GIM-UAT-SRV-01 | Medium
Monitor Alert | Backup Failure Moniotr Alert has been detected on resource AZ-VM-GIM-UAT-SRV-02 | Medium
Diagnostic Settings | No Azure Diagnostic Settings for Virtual Networks . It is recommended to to keep Virtual Networks Logs for Auditing and Investigations | Low
Diagnostic Settings | No Azure Diagnostic Settings for Network Security Groups . It is recommended to to keep NeMork Security Groups Logs for Auditing and Investigations | Low
Diagnostic Settings | No Azure Diagnostic Settings for Public lps . It is recommended to to keep Public lps Logs for Auditing and Investigations | Low

## PaySky-Customized-Recommendatio
Global Brands Group Azure Security Initial Finding and Recommendation-PaySky-Spoke Subscription
Scope of the finding and recommendation This document used to perform the assessment, analyze data, and prioritize findings, Include both negative and positive findings. Prioritize findings related to security risks and remediation steps. Provide a practical remediation path, accounting for the organization's strengths and weaknesses. |  | Customer Name : PaySky |  |  | Global Brands Group
Subscription Name: Spoke Subscription
Customer Primary Contact Name :
|  | Customer Primary Contact Email : |  |  | Cloud Security Engineer Name: Omar Sameh
|  | Start Date : 2-3-2025 |  |  | Cloud Security Team Lead: Marco Fekry
|  | Due Date : |  |  | Cloud Security Team Lead Email: Marco.Fekry@gbrands.com
Products | Recommendations | The Competent Authority | Risk Level | Estimated Cost | Recommendations Description | Remediation Refrence | Compliance % | Customer Acceptance | Cost Required | Cost Customer Acceptance | Customer Risk Acceptance | Completion % | Final Compliance | Engineer Comment
Identity | A maximum of 3 Owners should be designated for subscriptions | Global Brands Cloud Security Team | High | No Cost | Identity recommendations | Microsoft Cyber Security Reference Architecture |  |  | No
| Reissue authenticators for changed groups and accounts | Global Brands Cloud Security Team | High
| Guest accounts with write permissions on Azure resources should be removed | Global Brands Cloud Security Team | High
| Disabled accounts with owner permissions on Azure resources should be removed | Global Brands Cloud Security Team | High
| Disabled accounts with read and write permissions on Azure resources should be removed | Global Brands Cloud Security Team | High
| Guest accounts with owner permissions on Azure resources should be removed | Global Brands Cloud Security Team | High
| Guest accounts with read permissions on Azure resources should be removed | Global Brands Cloud Security Team | High
| The Unknown Azure Scoped type is Subscriptions while it should be limited to the intended resources permissions | Global Brands Cloud Security Team | High
Defender for cloud alerts and coverage | Defender For Cloud Should be Enabled on ContainerRegistry | Global Brands Cloud Security Team | High | 1 vcore x 1 Month x $0.0094 = $6.87 Monthly Cost | Defender for cloud coverage and alerts recommendations | Microsoft Cyber Security Reference Architecture |  |  | Yes
| Defender For Cloud Should be Enabled on Dns | Global Brands Cloud Security Team | High | 15.00$ / Month
| Defender For Cloud Aerts have been detected or the Product Microsoft Defender for Cloud logged to the resource AZ-AKS-GIM-LJAT | Global Brands Cloud Security Team | High | No Cost
Microsoft Sentinel | Microsoft Sentinel SEIM and SOAR Should be Enabled on All Available Data Sources | Global Brands Cloud Security Team | High | Analytics logs = $4.30 / 1 GB / Day Basic Logs = $1.00 / 1 GB / Day | Collect and analyze security logs, detect threats with AI, and automate incident response using playbooks. | Microsoft Cyber Security Reference Architecture |  |  | Yes
Azure Firewall | Azure Firewall is recommended to secure your Workloads , Or else use an Azure Marketplace Security Appiance | Global Brands Cloud Security Team | High | Standard = $1.25/ Hour, Monthly cost = $912.50 Premium = $1.75 / Hour, Monthly cost = $1,277.50 | Implement application and network rules to restrict traffic and enforce Zero Trust principles.
Web Application Firewall | Azure Web Appication Firewall is recornmended to secure your Workloads | Global Brands Cloud Security Team | High | WAF v2 1 capacity unit = Monthly cost $273.31 Note: Each capacity unit is composed of at most: 1 compute unit, or 2,500 persistent connections, or 2.22-Mbps throughput. If any one of these metrics are exceeded, then another n capacity unit(s) are necessary, even if the other two metrics don’t exceed this single capacity unit’s limits. | Configure managed rules to protect against OWASP Top 10 vulnerabilities and protect your websites
Azure DDOS | Azure DDOS is recomrnended to secure your Pudic IPs from Denial of Service Attacks | Global Brands Cloud Security Team | High | 1 IP address costs $199.00 / Month | Use Azure DDoS Protection Standard to mitigate large-scale attacks automatically
Azure Bastion | Azure Bastions is recommended to secure your Remote Desktop Protocol (RDP) and Secure Shell Protocol (SSH) access to virtual machines (VMs) without any exposure through public IP addresses | Global Brands Cloud Security Team | Low | Premium Tier Monthly cost = $328.50 | Restrict access using RBAC and enforce MFA for secure VM connections
Purview | Azure Purview Accounts is recommended to address the of data across organizations, lack of visibility that hampers data protection and governance | Global Brands Cloud Security Team | Low | For 1 hour scanning x 32 vcores x 0.011$ and 1 month Advanced Resource Set and Report Generation and 1 capacity unit x 1 month x 0.411$ = $1,072.09 Monthly cost Note: 1 Capacity Unit supports requests of up to 25 data map operations per second and includes storage of up to 10 GB of metadata about data assets | Enable data classification and sensitivity labels to prevent unauthorized data access.
Copilot | Microsoft Security Copilot is recommended to improve security outcomes at machine speed and scale, while remaining compliant to responsible Al principles. | Global Brands Cloud Security Team | Low | 1 Security compute units x 1 month x 4.00$ = $2,920.00 Monthly cost | Regularly review permissions and limit access to prevent unauthorized AI-generated actions.
Storage Accounts | gimpreprodsacc Storage Account Public Network Access should be disallowed, It is recommended to use private EndPoints to secure your data | Global Brands Cloud Security Team | High | Enabling private endpoint will costs money | Disable public access
Virtual Machines | 4 Virtual Machine Disks Encryption is recommended to secure your data | Global Brands Cloud Security Team | High | Will depend on type of encryption as SSE with Customer Key will cost money | Encrytion for disks | Microsoft Cyber Security Reference Architecture |  |  | Yes
| 4 Virtual Machine Disks Replication is recommended for High Availability of your workloads | Global Brands Cloud Security Team | High | If you enable disk replication in Azure, the cost depends on which type of replication you choose and which Azure services you use for that replication Ex: ASR, ZRS,GZRS | Covering failures by enabling ASR |  |  |  | Yes
SQL Databases | SQL Database Advanced Threat Protection disabled State detected, It is recommended to turn Advanced Threat Protection State On to secure your data | Global Brands Cloud Security Team | High | $15 USD per server per month | Enable advanced thread protection | Microsoft Cyber Security Reference Architecture |  |  | Yes
Key Vault | GIMPAY-KVO1 Key Vault Public Access has been detected, It is recommended to use private connectivity to secure your workloads | Global Brands Cloud Security Team | High | Will pay regarding Private Endpoint and Inbound/Outbound Data Transfer | Enabling private connectivity to secure your workloads | Microsoft Cyber Security Reference Architecture |  |  | Yes
Diagnostics | No Azure Diagnostic Settings for Virtual Networks, Public IPS and NSG | Global Brands Cloud Security Team | Low | For Virtual networks, public IPs it depends on Ingestion + Retention for log analyticsworkspace NSG Flow Logs Cost: $0.50 to $2 per GB (varies by region). Data ingestion (~$2.76 per GB in many regions). | This allows you to collect logs and metrics |  |  |  | Yes