## PaySky-Detailed Resources
Global Brands Group Azure Security Initial Finding and Recommendation- Hub Subscription
| Customer Name : Paysky |  | Global Brands Group
Customer Primary Contact Name : Omar Sameh
| Customer Primary Contact Email : Omar.Sameh@gbrands.com |  | Cloud Security Engineer Name: Omar Sameh
| Customer Secondary Contact Name : Sherif Nagy |  | Start Date : 3-3-2025
| Customer Secondary Contact Email : Sherif.Nagy@gbrands.com |  | Due Date :
| Start Date : 3-3-2025 |  | Cloud Security Team Lead: Marco Fekry
| Due Date : |  | Cloud Security Team Lead Email: Marco.Fekry@gbrands.com
Target Security Area | Detailed Resources Report Summary Findings | Severity
Virtual Machines | GIM-FGT-UAT Virtual Machine Disabled Linux Patch Mode detected | High
Virtual Machines | GIM-FGT-UAT Virtual Machine Disabled Linux Assessment Mode detected | High
Virtual Machines | GIM-FGT-UAT Virtual Machine No Trusted Launch detected | High
Virtual Machines | GIM-FGT-UAT Virtual Machine Disks Encryption is recommended to secure your data | High
Virtual Machines | GIM-FGT-UAT Virtual Machine Disks Replication is recommended for High Availability of your workloads | High
Network Security Groups | GIM-FGT-UAT Network Security Group * source detected | High
Subscriptions | Azure Subscription Diagnostic Settings is recommended to to keep Subscription Activity Logs for Auditing and Investigations | Low
Diagnostic Settings | No Azure Diagnostic Settings for Virtual Networks, Public IPS and NSG | Low
Diagnostic Settings | No Azure Diagnostic Settings for Public Ips . It is recommended to to keep Public Ips Logs for Auditing and Investigations | Low
Diagnostic Settings | No Azure Diagnostic Settings for Network Security Groups . It is recommended to to keep Network Security Groups Logs for Auditing and Investigations | Low

## PaySky-Customized-Recommendatio
Global Brands Group Azure Security Initial Finding and Recommendation-PaySky-Hub Subscription
Scope of the finding and recommendation This document used to perform the assessment, analyze data, and prioritize findings, Include both negative and positive findings. Prioritize findings related to security risks and remediation steps. Provide a practical remediation path, accounting for the organization's strengths and weaknesses. |  | Customer Name : PaySky |  |  | Global Brands Group
Subscription Name: Hub Subscription
Customer Primary Contact Name : Omar Sameh
|  | Customer Primary Contact Email : Omar.Sameh@gbrands.com |  |  | Cloud Security Engineer Name: Omar Sameh
|  | Start Date : 2-3-2025 |  |  | Cloud Security Team Lead: Marco Fekry
|  | Due Date : |  |  | Cloud Security Team Lead Email: Marco.Fekry@gbrands.com
Products | Recommendations | The Competent Authority | Risk Level | Estimated Cost | Recommendations Description | Remediation Refrence | Compliance % | Customer Acceptance | Cost Required | Cost Customer Acceptance | Customer Risk Acceptance | Completion % | Final Compliance | Engineer Comment
Identity | A maximum of 3 Owners should be designated for subscriptions | Global Brands Cloud Security Team | High | No Cost | Identity recommendations | Microsoft Cyber Security Reference Architecture |  |  | No
| Reissue authenticators for changed groups and accounts | Global Brands Cloud Security Team | High
| Guest accounts with write permissions on Azure resources should be removed | Global Brands Cloud Security Team | High
| Disabled accounts with owner permissions on Azure resources should be removed | Global Brands Cloud Security Team | High
| Disabled accounts with read and write permissions on Azure resources should be removed | Global Brands Cloud Security Team | High
| Guest accounts with owner permissions on Azure resources should be removed | Global Brands Cloud Security Team | High
| Guest accounts with read permissions on Azure resources should be removed | Global Brands Cloud Security Team | High
| The Unknown Azure Scoped type is Subscriptions while it should be limited to the intended resources permissions | Global Brands Cloud Security Team | High
Defender for cloud recommendations | 3 High Severity Defender for Cloud Recommendations Detected | Global Brands Cloud Security Team | High | No Cost | Defender for cloud coverage and alerts recommendations | Microsoft Cyber Security Reference Architecture |  |  | No
Azure Monitor | Azure Monitor is a recommended insights solution for Virtual Machines to keep track of Virtual Machine Insights | Global Brands Cloud Security Team | High | No Cost | Enable insights on the machines to keep tracking and monitoring | Microsoft Cyber Security Reference Architecture |  |  | No
Microsoft Sentinel | Microsoft Sentinel SEIM and SOAR Should be Enabled on All Available Data Sources | Global Brands Cloud Security Team | High | Analytics logs = $4.30 / 1 GB / Day Basic Logs = $1.00 / 1 GB / Day | Collect and analyze security logs, detect threats with AI, and automate incident response using playbooks. | Microsoft Cyber Security Reference Architecture |  |  | Yes
Azure Firewall | Azure Firewall is recommended to secure your Workloads (GIM-FGT-UAT with fortinet VM security appliance detected ) | Global Brands Cloud Security Team | High | Standard = $1.25/ Hour, Monthly cost = $912.50 Premium = $1.75 / Hour, Monthly cost = $1,277.50 | Enable Azure firewall to protect your workloads
Web Application Firewall | AZ-WAF-UAT-GIM Application Gateway Web Application Firewall RuleSetType OWASP rule Upgrade is recommended to Microsoft_BotManagerRuleSet in order to secure youe WAF Traffic | Global Brands Cloud Security Team | High | WAF v2 1 capacity unit = Monthly cost $273.31 Note: Each capacity unit is composed of at most: 1 compute unit, or 2,500 persistent connections, or 2.22-Mbps throughput. If any one of these metrics are exceeded, then another n capacity unit(s) are necessary, even if the other two metrics don’t exceed this single capacity unit’s limits. | Configure managed rules to protect against OWASP Top 10 vulnerabilities and protect your websites.
Web Application Firewall | AZ-AG-UAT-GIM Application Gateway Web Application Firewall Mode should be configured to Prevent Application Gateway Threats | Global Brands Cloud Security Team | High
Web Application Firewall | AZ-AG-UAT-GIM AppLication Gateway Diagnostics should be configured to keep track of our traffic insights and threats | Global Brands Cloud Security Team | High
Azure DDOS | Azure DDOS is recomrnended to secure your Pudic IPs from Denial of Service Attacks | Global Brands Cloud Security Team | High | 1 IP address costs $199.00 / Month | Use Azure DDoS Protection Standard to mitigate large-scale attacks automatically
Azure Bastion | Azure Bastions is recommended to secure your Remote Desktop Protocol (RDP) and Secure Shell Protocol (SSH) access to virtual machines (VMs) without any exposure through public IP addresses | Global Brands Cloud Security Team | Low | Premium Tier Monthly cost = $328.50 | Restrict access using RBAC and enforce MFA for secure VM connections
Purview | Azure Purview Accounts is recommended to address the of data across organizations, lack of visibility that hampers data protection and governance | Global Brands Cloud Security Team | Low | For 1 hour scanning x 32 vcores x 0.011$ and 1 month Advanced Resource Set and Report Generation and 1 capacity unit x 1 month x 0.411$ = $1,072.09 Monthly cost Note: 1 Capacity Unit supports requests of up to 25 data map operations per second and includes storage of up to 10 GB of metadata about data assets | Enable data classification and sensitivity labels to prevent unauthorized data access.
Copilot | Microsoft Security Copilot is recommended to improve security outcomes at machine speed and scale, while remaining compliant to responsible Al principles. | Global Brands Cloud Security Team | Low | 1 Security compute units x 1 month x 4.00$ = $2,920.00 Monthly cost | Regularly review permissions and limit access to prevent unauthorized AI-generated actions.
Defender EASM | Defender EASM is recommended to continuously discovers and maps your digital attack surface to provide an external view of your online infrastructure | Global Brands Cloud Security Team | Low | 1 IP address, Domain, Hosts x 1 Month x 0.011$ /Day = $0.99 Monthly Cost | Enable to discovers and maps your digital attack surface to provide an external view of your online infrastructure
Virtual Machines | GIM-FGT-UAT Virtual Machine No Trusted Launch detected | Global Brands Cloud Security Team | High | Create a new disk or convert your existing disk into a Trusted Launch-compatible disk If you resize the VM this might change pricing. | Trusted launch security machines to protect your operating systems |  |  |  | Yes
| GIM-FGT-UAT Virtual Machine Disks Replication is recommended for High Availability of your workloads | Global Brands Cloud Security Team | High | If you enable disk replication in Azure, the cost depends on which type of replication you choose and which Azure services you use for that replication Ex: ASR, ZRS,GZRS | Covering failures by enabling ASR |  |  |  | Yes
| GIM-FGT-UAT Virtual Machine Disks Encryption is recommended to secure your data | Global Brands Cloud Security Team | High | Will depend on type of encryption as SSE with Customer Key will cost money | Encrytion for disks |  |  |  | Yes
Subscription | Azure Subscription Diagnostic Settings is recommended to to keep Subscription Activity Logs for Auditing and Investigations | Global Brands Cloud Security Team | Low | Sending to log analytics workspace $2.76 per GB ingested (varies by region) Retention beyond the first 31 days also costs extra | This allows you to collect logs and metrics |  |  |  | Yes
Diagnostics | No Azure Diagnostic Settings for Virtual Networks, Public IPS and NSG | Global Brands Cloud Security Team | Low | For Virtual networks, public IPs it depends on Ingestion + Retention for log analyticsworkspace NSG Flow Logs Cost: $0.50 to $2 per GB (varies by region). Data ingestion (~$2.76 per GB in many regions). | This allows you to collect logs and metrics |  |  |  | Yes